## Discovery Interviews
Interview ID | Stakeholder Type | Organisation / School | Interviewee Name | Country | Sector | Date | Key Themes | Pain Points | Opportunities | Follow-ups | Satisfaction (1-5) | Priority Level | Linked File
INT-001 | Org Admin | GreenCycle Cooperative | Mrs. Olufunke Adewale | Nigeria | Recycling Cooperative | 08-Nov-2025 | Membership enrolment, learning access, reporting | Manual paper records; no centralised tracking; difficulty monitoring training completion. | Introduce member portal with online training, attendance, and simple reports. | Schedule demo of proposed platform for cooperative leadership. | 3 | High | Stakeholder_Interview_Notes\OrgAdmin_Interview_01.docx
INT-002 | Instructor | Manchester AgriHub | Sarah Jones | UK | Agriculture Training | 09-Nov-2025 | Course creation, media upload, rural learner access | Slow video uploads; learners with poor bandwidth struggle to stream content. | Add adaptive video streaming, downloadable resources, and compressed formats. | Test pilot course with low-bandwidth configuration. | 4 | High | Stakeholder_Interview_Notes\Instructor_Interview_02.docx
INT-003 | Student | Unique Youth Enterprise Centre | Adeyemi Tunde | Nigeria | Entrepreneurship | 10-Nov-2025 | Mobile learning, certificates, affordability | Can’t afford data-heavy platforms; progress tracking unclear. | Lightweight mobile-friendly learner interface, offline notes, clear certificate display. | Collect feedback from 20+ youth learners after pilot. | 5 | Medium | Stakeholder_Interview_Notes\Student_Interview_03.docx
INT-004 | DMP / Compliance | ReGreen Agro Solutions Ltd | Dr. Fiona Clark | UK | Agri Data & Training | 10-Nov-2025 | GDPR, audit trails, data sharing | No unified view of where learner data sits; weak audit logging. | Implement clear data ownership model, RLS by org, immutable audit logs. | Draft Data Protection Impact Assessment (DPIA) based on proposed architecture. | 4 | High | Stakeholder_Interview_Notes\DMP_Compliance_Interview_04.docx
INT-005 | Executive Sponsor | Unique Cooperative Society | Mr. Chukwuma Eze | Nigeria | Cooperative & Microfinance | 11-Nov-2025 | Impact tracking, KPIs, financial sustainability | No structured way to see how training affects loan performance or member growth. | Dashboards linking course completion to member retention and repayment behaviour. | Define KPI framework and reporting cadence for ExCo. | 3 | High | Stakeholder_Interview_Notes\ExecSponsor_Interview_05.docx
INT-006 | Technical Lead | EcoFarm Learning UK | James Bennett | UK | AgriTech Education | 12-Nov-2025 | Integration, uptime, connectivity constraints | Rural sites with unstable internet; need secure SSO and simple integrations. | Hybrid-friendly cloud setup, robust API, offline-tolerant client patterns. | Run technical feasibility workshop with platform engineering team. | 4 | Medium | Stakeholder_Interview_Notes\TechLead_Interview_06.docx