## Slide 1: Phase 1 Kick-off – Unique Entrepreneur Literacy Hub
Agenda:
1. Vision & Background
2. Goals & Success Criteria
3. Scope Overview
4. Roles & Responsibilities
5. Discovery Plan & Deliverables
6. Risks & Next Steps
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 2: Project Vision
To design and deliver a scalable, secure learning / data platform for Unique Entrepreneur Solutions Limited,
enabling governed, insight-driven experiences for learners and stakeholders.
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 3: Problem Statement / Opportunity
Current landscape:
- Fragmented tools and manual processes
- Limited visibility across tenants / teams
- Governance and compliance overhead
Opportunity:
- One governed platform that unifies delivery, reporting, and experience.
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 4: Goals & Success Metrics
- MVP live by Month 7 – ≥ 3 pilot organisations
- Completion rate ≥ 80 %
- ≥ 5 monetised offerings (if applicable)
- DPIA / GDPR / security checks passed pre-launch
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 5: Scope Overview (MVP)
In Scope:
- Tenant / organisation hierarchy & access control
- Core feature set (content, enrolment, tracking)
- Essential reports & dashboards
- Secure authentication / roles
Out of Scope (Phase 1):
- Advanced AI and non-priority integrations
- Full mobile/offline build
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 6: Roles & Responsibilities
- Business Analysis – Omole Victoria Oluwatosin
- Data & Reporting – Omole Victoria Oluwatosin
- Data Governance & Compliance – Omole Victoria Oluwatosin
- Product / Engineering – To be confirmed with {cfg['client']}
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 7: Discovery Plan (3 Weeks)
Week 1 – Stakeholders, current-state, risks
Week 2 – Interviews, journeys, requirements
Week 3 – Target vision, MVP, roadmap, sign-off
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 8: Governance & Compliance Preview
Focus Areas:
- Ownership, roles & responsibilities
- Access controls & segregation of data
- DPIA / GDPR, retention, consent
- Logging, audit, incident response
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 9: Analytics & KPI Preview
Example KPIs:
- Active users by tenant
- Enrolment vs completion
- Engagement by course / cohort
- Support tickets & issues
- Adoption trend over time
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 10: Initial Risks & Assumptions
Examples (customise per client):
- Access to existing systems / data delayed
- Limited SME availability for discovery
- Integration complexity higher than expected
- Assumption: scope disciplined around MVP
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 11: Next Steps & Action Owners
- Circulate minutes & deck – Omole Victoria Oluwatosin (+1 day)
- Confirm stakeholders & interview slots – Client / BA (+2–3 days)
- Share existing documentation & system access – Client (+3 days)
- Agree MVP scope & timeline – Joint sign-off
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance

## Slide 12: Q & A / Wrap-Up
Confirm shared understanding
Capture decisions and open points
Formally launch Discovery / Phase
Omole Victoria Oluwatosin — Business Analyst | Data / Reporting | Data Governance