## Slide 1: Phase 1 Kick-off – Unique Entrepreneur Literacy Hub
Agenda:
1. Vision & Background
2. Goals & Success Criteria
3. Scope Overview
4. Roles & Responsibilities
5. Discovery Plan & Deliverables
6. Risks & Next Steps
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 2: Project Vision
To build a scalable multi-tenant learning ecosystem enabling individuals and organisations to deliver, manage, and learn effectively online.
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 3: Problem Statement / Opportunity
Existing LMS tools lack flexible tenancy or white-labelling.
Schools manage fragmented systems.
Learners want credentials and accessibility.
Opportunity: One secure platform bridging commerce & education.
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 4: Goals & Success Metrics
MVP live by Month 7 – ≥ 3 pilot organisations
Boost engagement – ≥ 80 % completion
Instructor monetisation – ≥ 5 paid courses
Governance – GDPR sign-off pre-launch
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 5: Scope Overview
In Scope (MVP): Multi-tenant org/school hierarchy, Course builder, Payments, Student player, Basic dashboard
Out of Scope: AI quiz generation, SCORM/xAPI support, Offline mobile mode
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 6: Roles & Responsibilities
Business Analyst – Omole Victoria Oluwatosin
Data Analyst – Omole Victoria Oluwatosin
Data Management Professional – Omole Victoria Oluwatosin
Frontend & Backend Engineer – Omole Victoria Oluwatosin
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 7: Discovery Plan (3 Weeks)
Week 1 – Kick-off & Stakeholder mapping
Week 2 – Interviews & Persona development
Week 3 – Vision + MVP definition + Sign-off
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 8: Governance & Compliance Preview
RLS for tenant data isolation
GDPR & DPIA
Data dictionary & retention policies
Consent management for analytics cookies
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 9: Analytics & KPI Preview
Active learners per org/school
Course completion rate
Instructor earnings & payouts
Engagement trend over time
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 10: Initial Risks & Assumptions
SSO complexity – High – Proof-of-concept early
GDPR delay – Medium – Legal review Week 2
Payment gateway setup – Medium – Sandbox by Week 3
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 11: Next Steps & Action Owners
Circulate minutes + slides – BA (+1 day)
Schedule interviews – BA (+2 days)
Draft governance overview – DMP (+3 days)
Define KPI list – DA + BA (+5 days)
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer

## Slide 12: Q & A / Wrap-Up
Confirm understanding & next steps
Thank attendees
Officially start Phase 1 Discovery
Omole Victoria Oluwatosin — Business Analyst | Data Analyst | Data Management Professional | Frontend & Backend Engineer